# Multi-Tenant Application - Detailed Project Timeline & Phases

## 📋 Executive Summary

**Project Name:** Multi-Tenant Portfolio Issue Tracking System

**Total Duration:** 8-10 Weeks (40-50 Business Days)

**Team Size:** 2-3 Developers (1 Full-stack + 1 Frontend + 1 Optional Backend)

**Deployment:** Cloud-based (Vercel + Railway + Supabase)

**Cost:** FREE Tier (Production-ready)

---

## 🎯 Project Phases Overview

```

┌────────────────────────────────────────────────────────────────┐

│                    PROJECT TIMELINE                            │

├────────────────────────────────────────────────────────────────┤

│ Phase 1: Project Setup & Planning         │ 1 Week  │  5 days │

│ Phase 2: Database & Backend Foundation    │ 2 Weeks │ 10 days │

│ Phase 3: Authentication System            │ 1 Week  │  5 days │

│ Phase 4: Tenant Management                │ 1 Week  │  5 days │

│ Phase 5: Core Features - Portfolios       │ 1 Week  │  5 days │

│ Phase 6: Core Features - Issue Tracking   │ 2 Weeks │ 10 days │

│ Phase 7: Analytics & Reporting            │ 1 Week  │  5 days │

│ Phase 8: Admin Panel & Super Admin        │ 1 Week  │  5 days │

│ Phase 9: Testing & Quality Assurance      │ 1 Week  │  5 days │

│ Phase 10: Deployment & Go-Live            │ 1 Week  │  5 days │

├────────────────────────────────────────────────────────────────┤

│ TOTAL                                      │ 10 Weeks│ 50 days │

└────────────────────────────────────────────────────────────────┘

⚠️ Note: Timeline assumes 1 full-stack developer working full-time

With 2-3 developers, timeline can be reduced to 6-7 weeks

```

---

## 📅 Detailed Phase Breakdown

---

## **Phase 1: Project Setup & Planning (Week 1)**

**Duration:** 5 Business Days

**Team:** Full-stack Developer

**Deliverables:** Project structure, development environment, documentation

### Day 1: Monday - Environment Setup (8 hours)

**Morning (4 hours):**

- ☐ Install required software:

- Node.js 18.x LTS

- Git

- VS Code or preferred IDE

- PostgreSQL (local, optional)

- ☐ Create GitHub repository

- ☐ Initialize Git repository

- ☐ Setup .gitignore files

- ☐ Create project README.md

**Afternoon (4 hours):**

- ☐ Create root project folder structure

- ☐ Initialize frontend project (React + TypeScript):

```bash

npx create-react-app client --template typescript

cd client && npm install

```

- ☐ Initialize backend project (Node.js + TypeScript):

```bash

mkdir server && cd server

npm init -y

npm install express typescript @types/node @types/express

npx tsc --init

```

- ☐ Configure TypeScript for both projects

**Deliverables:**

- ✅ Working development environment

- ✅ Git repository initialized

- ✅ Basic project structure created

---

### Day 2: Tuesday - Supabase & Database Setup (8 hours)

**Morning (4 hours):**

- ☐ Create Supabase account (https://supabase.com)

- ☐ Create new Supabase project

- ☐ Note down API keys (URL, anon key, service key)

- ☐ Create database schema documentation

- ☐ Design ER diagram (using draw.io or similar)

**Afternoon (4 hours):**

- ☐ Create migration files (in `/database/migrations/`):

- `001_create_tenants.sql`

- `002_create_users.sql`

- `003_create_portfolios.sql`

- `004_create_issues.sql`

- `005_create_hour_reservations.sql`

- `006_create_admin_logs.sql`

- `007_create_monitored_personnel.sql`

- `008_create_subscriptions.sql`

- ☐ Run migrations in Supabase SQL Editor

- ☐ Verify all tables created successfully

- ☐ Test database connection from Node.js

**Deliverables:**

- ✅ Supabase project created

- ✅ Database schema implemented

- ✅ All tables created with relationships

---

### Day 3: Wednesday - Dependencies & Configuration (8 hours)

**Morning (4 hours):**

- ☐ Install frontend dependencies:

```bash

cd client

npm install axios react-router-dom

npm install @tanstack/react-query zustand

npm install react-hook-form date-fns

npm install chart.js react-chartjs-2

npm install react-hot-toast

npm install -D tailwindcss postcss autoprefixer

npx tailwindcss init -p

```

- ☐ Configure Tailwind CSS

- ☐ Setup CSS variables and theme

- ☐ Create global styles

**Afternoon (4 hours):**

- ☐ Install backend dependencies:

```bash

cd server

npm install express cors dotenv

npm install @supabase/supabase-js

npm install bcrypt jsonwebtoken

npm install express-validator express-rate-limit

npm install winston

npm install -D nodemon ts-node

npm install -D @types/cors @types/bcrypt @types/jsonwebtoken

```

- ☐ Create .env files (frontend & backend)

- ☐ Setup environment variable templates

- ☐ Configure nodemon for auto-restart

- ☐ Test basic Express server

**Deliverables:**

- ✅ All dependencies installed

- ✅ Configuration files created

- ✅ Environment variables configured

---

### Day 4: Thursday - Folder Structure & Boilerplate (8 hours)

**Morning (4 hours):**

- ☐ Create complete frontend folder structure:

```

client/src/

├── components/

├── hooks/

├── context/

├── services/

├── utils/

├── types/

└── styles/

```

- ☐ Create boilerplate components:

- Button.tsx

- Input.tsx

- Modal.tsx

- Spinner.tsx

- Toast.tsx

- ☐ Setup React Router structure

- ☐ Create layout components (Navbar, Sidebar, Footer)

**Afternoon (4 hours):**

- ☐ Create complete backend folder structure:

```

server/src/

├── config/

├── routes/

├── controllers/

├── services/

├── middleware/

├── models/

├── utils/

└── validators/

```

- ☐ Create basic middleware:

- errorHandler.middleware.ts

- logger.middleware.ts

- cors.middleware.ts

- ☐ Setup Winston logger

- ☐ Create database connection utility

**Deliverables:**

- ✅ Complete folder structure

- ✅ Boilerplate files created

- ✅ Basic utilities implemented

---

### Day 5: Friday - Documentation & Planning Review (8 hours)

**Morning (4 hours):**

- ☐ Create API documentation template

- ☐ Write setup instructions (README.md)

- ☐ Document environment variables

- ☐ Create development workflow guide

- ☐ Setup ESLint and Prettier

- ☐ Configure pre-commit hooks (optional)

**Afternoon (4 hours):**

- ☐ Review entire setup with team

- ☐ Test development environment

- ☐ Fix any configuration issues

- ☐ Create development branch strategy

- ☐ Setup project management board (Jira/Trello/GitHub Projects)

- ☐ Plan Sprint 1 tasks

**Deliverables:**

- ✅ Complete documentation

- ✅ Working development environment

- ✅ Ready to start development

**Phase 1 Completion Checklist:**

- ✅ Development environment ready

- ✅ Database schema created

- ✅ All dependencies installed

- ✅ Folder structure complete

- ✅ Documentation written

---

## **Phase 2: Database & Backend Foundation (Weeks 2-3)**

**Duration:** 10 Business Days

**Team:** Backend Developer (or Full-stack)

**Deliverables:** Complete backend API foundation, database with RLS

### Week 2, Day 1-2: Monday-Tuesday - Database Advanced Setup (16 hours)

**Day 1 Morning (4 hours):**

- ☐ Create Row Level Security (RLS) policies:

```sql

-- Enable RLS on all tables

ALTER TABLE tenants ENABLE ROW LEVEL SECURITY;

ALTER TABLE users ENABLE ROW LEVEL SECURITY;

-- (Continue for all tables)

```

- ☐ Create tenant isolation policies

- ☐ Test RLS policies with sample data

**Day 1 Afternoon (4 hours):**

- ☐ Create database indexes for performance:

```sql

CREATE INDEX idx_users_tenant_id ON users(tenant_id);

CREATE INDEX idx_portfolios_tenant_id ON portfolios(tenant_id);

CREATE INDEX idx_issues_tenant_id ON issues(tenant_id);

-- (Continue for all foreign keys)

```

- ☐ Create database functions (if needed)

- ☐ Setup database triggers (updated_at timestamps)

**Day 2 Morning (4 hours):**

- ☐ Create seed data for development:

- Sample tenant (Test Company)

- Sample users (admin, user1, user2)

- Sample portfolios (5-10 portfolios)

- Sample issues (20-30 issues)

- ☐ Run seed scripts

- ☐ Verify data integrity

**Day 2 Afternoon (4 hours):**

- ☐ Create database backup/restore scripts

- ☐ Document database schema

- ☐ Create ER diagram (if not done in Phase 1)

- ☐ Test database performance

---

### Week 2, Day 3-5: Wednesday-Friday - Core Backend Middleware (24 hours)

**Day 3 (8 hours):**

- ☐ **Authentication Middleware** (auth.middleware.ts):

- JWT token verification

- Token extraction from headers

- User lookup from token

- Attach user to request object

- Handle expired tokens

- Handle invalid tokens

- ☐ Write unit tests for auth middleware

- ☐ Test with sample tokens

**Day 4 (8 hours):**

- ☐ **Tenant Isolation Middleware** (tenantIsolation.middleware.ts):

- Extract tenant_id from JWT token

- Attach tenant_id to request

- Verify user belongs to tenant

- Block cross-tenant access attempts

- Log isolation violations

- ☐ Write unit tests for tenant isolation

- ☐ Test with multiple tenants

**Day 5 (8 hours):**

- ☐ **Validation Middleware** (validation.middleware.ts):

- Input sanitization

- Data type validation

- Required fields validation

- Email format validation

- Password strength validation

- ☐ **Rate Limiting Middleware** (rateLimiter.middleware.ts):

- Rate limits per endpoint

- IP-based limiting

- User-based limiting

- Custom error messages

- ☐ **Permission Middleware** (permission.middleware.ts):

- Role-based access control

- Permission checks

- ☐ Test all middleware

---

### Week 3, Day 1-2: Monday-Tuesday - Core Backend Services (16 hours)

**Day 1 (8 hours):**

- ☐ Create Supabase client utility (supabase.util.ts)

- ☐ Create password hashing utilities (password.util.ts):

- Hash password (bcrypt)

- Compare password

- Generate random password

- ☐ Create JWT utilities (jwt.util.ts):

- Generate access token

- Generate refresh token

- Verify token

- Decode token

- ☐ Create email utilities (email.util.ts):

- Send welcome email

- Send password reset email

- Email templates

**Day 2 (8 hours):**

- ☐ Create validation utilities (validation.util.ts):

- Email validation

- Password validation

- UUID validation

- Date validation

- ☐ Create logger utility (logger.util.ts):

- Winston logger setup

- Log levels (error, warn, info, debug)

- Log to file

- Log to console

- ☐ Create date utilities (date.util.ts):

- Format dates

- Calculate date ranges

- Timezone handling

---

### Week 3, Day 3-5: Wednesday-Friday - Database Models & Error Handling (24 hours)

**Day 3 (8 hours):**

- ☐ Create TypeScript interfaces for all tables:

- tenant.model.ts

- user.model.ts

- portfolio.model.ts

- issue.model.ts

- reservation.model.ts

- adminLog.model.ts

- monitoredPersonnel.model.ts

- subscription.model.ts

- ☐ Create request/response types

- ☐ Create error types

**Day 4 (8 hours):**

- ☐ Create custom error classes:

- BadRequestError (400)

- UnauthorizedError (401)

- ForbiddenError (403)

- NotFoundError (404)

- ConflictError (409)

- InternalServerError (500)

- ☐ Create error handler middleware

- ☐ Implement global error handling

- ☐ Test error scenarios

**Day 5 (8 hours):**

- ☐ Setup request logging (Winston)

- ☐ Setup error logging

- ☐ Configure log rotation

- ☐ Test entire backend foundation

- ☐ Fix any bugs found

- ☐ Code review and refactoring

**Phase 2 Completion Checklist:**

- ✅ Database with RLS fully configured

- ✅ All middleware implemented and tested

- ✅ Utilities created

- ✅ Error handling implemented

- ✅ Logging configured

---

## **Phase 3: Authentication System (Week 4)**

**Duration:** 5 Business Days

**Team:** Full-stack Developer

**Deliverables:** Complete email-based authentication system

### Day 1: Monday - Backend Auth Routes & Controllers (8 hours)

**Morning (4 hours):**

- ☐ Create auth routes (auth.routes.ts):

```

POST /api/auth/register

POST /api/auth/login

POST /api/auth/logout

POST /api/auth/refresh

POST /api/auth/forgot-password

POST /api/auth/reset-password

GET  /api/auth/me

```

- ☐ Setup route handlers structure

**Afternoon (4 hours):**

- ☐ Create auth controller (auth.controller.ts):

- Register function

- Login function

- Logout function

- Refresh token function

- Get current user function

- ☐ Link routes to controllers

- ☐ Test routes with Postman/Insomnia

---

### Day 2: Tuesday - Auth Service Layer (8 hours)

**Morning (4 hours):**

- ☐ Create auth service (auth.service.ts):

- **Register user:**

- Validate email format

- Check if email already exists

- Hash password with bcrypt

- Create user record with tenant_id

- Send welcome email

- Return success message

- **Login user:**

- Find user by email

- Check user is_active = true

- Verify password

- Update last_login timestamp

- Generate JWT token with tenant_id

- Return token

**Afternoon (4 hours):**

- ☐ Implement:

- **Logout user:**

- Invalidate token (optional: blacklist)

- Clear session

- **Refresh token:**

- Verify refresh token

- Generate new access token

- Return new token

- **Forgot password:**

- Validate email

- Generate reset token

- Send reset email

- **Reset password:**

- Verify reset token

- Validate new password

- Hash and update password

- ☐ Test all auth functions

---

### Day 3: Wednesday - Frontend Auth UI Components (8 hours)

**Morning (4 hours):**

- ☐ Create UserLogin.tsx component:

- Email input field ✅ (changed from username)

- Password input field

- "Remember me" checkbox (optional)

- "Forgot password?" link

- "Login" button

- "Switch to Admin Login" button

- Form validation

- Error handling

- Loading state

**Afternoon (4 hours):**

- ☐ Create AdminLogin.tsx component:

- Email input field ✅ (changed from username)

- Password input field

- "Login as Admin" button

- "Switch to User Login" button

- Form validation

- Error handling

- ☐ Create ForgotPassword.tsx component:

- Email input

- Submit button

- Success/error messages

---

### Day 4: Thursday - Frontend Auth Context & API Integration (8 hours)

**Morning (4 hours):**

- ☐ Create AuthContext (AuthContext.tsx):

- Auth state management

- User state

- Tenant state

- Login function

- Logout function

- Register function

- Check authentication status

- Auto-refresh token

- ☐ Create useAuth hook (useAuth.ts)

- ☐ Wrap App.tsx with AuthContext

**Afternoon (4 hours):**

- ☐ Create auth API service (authService.ts):

- register(email, password, fullName)

- login(email, password)

- logout()

- refreshToken()

- forgotPassword(email)

- resetPassword(token, newPassword)

- getCurrentUser()

- ☐ Integrate with Axios

- ☐ Setup Axios interceptors for token refresh

- ☐ Test authentication flow end-to-end

---

### Day 5: Friday - Session Management & Testing (8 hours)

**Morning (4 hours):**

- ☐ Implement session management:

- Store JWT token in localStorage/sessionStorage

- Auto-logout after 8 hours (users)

- Auto-logout after 2 hours (admins)

- Session expiry warnings

- Prevent false logouts

- Multi-tab session sync

- ☐ Create PrivateRoute component

- ☐ Protect all routes requiring authentication

**Afternoon (4 hours):**

- ☐ Test authentication flows:

- User registration (with email)

- User login (with email)

- Admin login (with email)

- Logout

- Token refresh

- Forgot password

- Reset password

- Session expiry

- ☐ Fix bugs

- ☐ Write unit tests for auth functions

**Phase 3 Completion Checklist:**

- ✅ Email-based authentication working ✅

- ✅ User and Admin login separate

- ✅ JWT tokens generated with tenant_id

- ✅ Session management implemented

- ✅ Password reset flow working

- ✅ All auth tests passing

---

## **Phase 4: Tenant Management (Week 5)**

**Duration:** 5 Business Days

**Team:** Full-stack Developer

**Deliverables:** Super Admin portal for managing tenants

### Day 1: Monday - Backend Tenant API (8 hours)

**Morning (4 hours):**

- ☐ Create tenant routes (tenant.routes.ts):

```

GET    /api/tenants          (list all - super admin only)

POST   /api/tenants          (create tenant)

GET    /api/tenants/:id      (get tenant details)

PUT    /api/tenants/:id      (update tenant)

DELETE /api/tenants/:id      (delete tenant)

GET    /api/tenants/:id/stats (tenant statistics)

```

**Afternoon (4 hours):**

- ☐ Create tenant controller (tenant.controller.ts)

- ☐ Create tenant service (tenant.service.ts):

- Create tenant (with subdomain generation)

- Update tenant

- Delete tenant (soft delete)

- Get tenant by ID

- List all tenants

- Get tenant statistics

- ☐ Add super admin permission check

---

### Day 2: Tuesday - Frontend Super Admin Dashboard (8 hours)

**Morning (4 hours):**

- ☐ Create SuperAdminDashboard.tsx:

- Total tenants (active/inactive)

- Total users across all tenants

- Total issues logged

- System health metrics

- Recent activity

- ☐ Create TenantList.tsx:

- Table showing all tenants

- Columns: Name, Subdomain, Status, Created, Users, Issues

- Search/filter functionality

- Sort functionality

**Afternoon (4 hours):**

- ☐ Create TenantForm.tsx (Add/Edit tenant):

- Company name input

- Contact email input

- Subdomain input (auto-generate from name)

- Logo upload

- Subscription plan dropdown

- Status dropdown

- Custom settings (JSON editor or form)

- Validation

- ☐ Create TenantDetails.tsx:

- Full tenant information

- List of users in tenant

- Statistics

- Edit/Delete buttons

---

### Day 3: Wednesday - Subdomain Routing & Tenant Detection (8 hours)

**Morning (4 hours):**

- ☐ Implement subdomain detection:

- Extract subdomain from URL

- Look up tenant by subdomain

- Set tenant context

- Redirect if tenant not found

- ☐ Configure DNS (if using custom domain)

- ☐ Test subdomain routing:

- client1.yourapp.com

- client2.yourapp.com

- admin.yourapp.com (super admin)

**Afternoon (4 hours):**

- ☐ Create TenantContext (TenantContext.tsx):

- Current tenant state

- Tenant loading state

- Detect tenant from subdomain

- Fetch tenant details

- Provide tenant to all components

- ☐ Create useTenant hook (useTenant.ts)

- ☐ Wrap App with TenantContext

- ☐ Test tenant detection

---

### Day 4: Thursday - Tenant API Integration & Testing (8 hours)

**Morning (4 hours):**

- ☐ Create tenant API service (tenantService.ts):

- createTenant(data)

- updateTenant(id, data)

- deleteTenant(id)

- getTenant(id)

- listTenants(filters)

- getTenantStats(id)

- ☐ Integrate with backend API

- ☐ Test CRUD operations

**Afternoon (4 hours):**

- ☐ Test tenant isolation:

- User A (Tenant A) logs in

- Verify sees only Tenant A data

- User B (Tenant B) logs in

- Verify sees only Tenant B data

- Verify cross-tenant access blocked

- ☐ Test super admin access:

- Can view all tenants

- Can edit any tenant

- Can delete tenants

- ☐ Fix any bugs found

---

### Day 5: Friday - Tenant Onboarding & Documentation (8 hours)

**Morning (4 hours):**

- ☐ Create tenant onboarding flow:

- Super admin creates tenant

- System generates subdomain

- System creates default admin user for tenant

- Send welcome email to tenant with credentials

- Tenant admin logs in

- Setup wizard (optional)

- ☐ Test onboarding flow end-to-end

**Afternoon (4 hours):**

- ☐ Document tenant management:

- How to add new tenant

- Subdomain configuration

- Tenant settings explanation

- Subscription plans

- ☐ Create admin user guide

- ☐ Test all tenant features

- ☐ Code review

**Phase 4 Completion Checklist:**

- ✅ Tenant CRUD operations working

- ✅ Subdomain routing configured

- ✅ Tenant isolation verified

- ✅ Super admin portal functional

- ✅ Onboarding flow tested

---

## **Phase 5: Core Features - Portfolios (Week 6)**

**Duration:** 5 Business Days

**Team:** Full-stack Developer

**Deliverables:** Complete portfolio management with locking

### Day 1: Monday - Backend Portfolio API (8 hours)

**Morning (4 hours):**

- ☐ Create portfolio routes (portfolio.routes.ts):

```

GET    /api/portfolios

POST   /api/portfolios

GET    /api/portfolios/:id

PUT    /api/portfolios/:id

DELETE /api/portfolios/:id

PUT    /api/portfolios/:id/status

POST   /api/portfolios/:id/lock

DELETE /api/portfolios/:id/unlock

```

**Afternoon (4 hours):**

- ☐ Create portfolio controller & service:

- List portfolios (filtered by tenant_id)

- Create portfolio (with tenant_id)

- Update portfolio

- Delete portfolio

- Update "all sites checked" status

- Lock portfolio (hour-based reservation)

- Unlock portfolio

- ☐ Add validation middleware

- ☐ Test with Postman

---

### Day 2: Tuesday - Frontend Portfolio UI (8 hours)

**Morning (4 hours):**

- ☐ Create PortfolioList.tsx:

- Grid/list view of portfolios

- Search bar

- Filter options

- Sort options

- ☐ Create PortfolioCard.tsx:

- Portfolio name

- Subtitle

- Site range

- "All Sites Checked" status indicator

- Lock indicator

- Quick actions (Edit, Delete, Log Issue)

**Afternoon (4 hours):**

- ☐ Create PortfolioForm.tsx:

- Name input (required)

- Subtitle input (optional)

- Site range input (optional)

- Validation

- Submit/Cancel buttons

- ☐ Create PortfolioDetails.tsx:

- Full portfolio information

- Issue history for this portfolio

- Edit/Delete buttons

---

### Day 3: Wednesday - Portfolio Locking System (8 hours)

**Morning (4 hours):**

- ☐ Implement backend locking:

- Create hour_reservations table entry

- Set expiration time (e.g., 30 minutes)

- Prevent duplicate locks

- Auto-cleanup expired locks

- ☐ Create lock/unlock API endpoints

- ☐ Test locking logic

**Afternoon (4 hours):**

- ☐ Implement frontend locking:

- Lock portfolio when "Log Issue" clicked

- Show lock indicator

- Disable portfolio for other users

- Show who locked and when

- Unlock on issue submit

- Unlock on cancel

- Handle lock expiration

- ☐ Test locking from multiple users

---

### Day 4: Thursday - "All Sites Checked" Feature (8 hours)

**Morning (4 hours):**

- ☐ Backend API for status update:

- Update all_sites_checked field (Yes/No/Pending)

- Update all_sites_checked_hour

- Update all_sites_checked_date

- Update all_sites_checked_by

- Update sites_checked_details (if "No")

- ☐ Test status updates

**Afternoon (4 hours):**

- ☐ Frontend status UI:

- Status dropdown (Yes/No/Pending)

- Hour selector (0-23)

- Date picker

- "Checked by" dropdown

- "Sites checked details" textarea (shown if "No" selected)

- Save button

- Visual status indicators (Green/Red/Gray)

- ☐ Test status updates from UI

---

### Day 5: Friday - Portfolio Testing & Polish (8 hours)

**Morning (4 hours):**

- ☐ Test all portfolio features:

- Create portfolio

- Edit portfolio

- Delete portfolio

- Search portfolios

- Filter portfolios

- Lock/unlock portfolio

- Update status

- ☐ Test tenant isolation (portfolios)

- ☐ Fix bugs

**Afternoon (4 hours):**

- ☐ Add animations and transitions

- ☐ Improve UI/UX

- ☐ Add loading states

- ☐ Add error handling

- ☐ Write unit tests

- ☐ Code review

**Phase 5 Completion Checklist:**

- ✅ Portfolio CRUD working

- ✅ Locking system functional

- ✅ "All Sites Checked" status working

- ✅ Tenant isolation verified

- ✅ UI polished

---

## **Phase 6: Core Features - Issue Tracking (Weeks 7-8)**

**Duration:** 10 Business Days

**Team:** Full-stack Developer

**Deliverables:** Complete issue tracking system

### Week 7, Day 1-2: Monday-Tuesday - Backend Issue API (16 hours)

**Day 1 (8 hours):**

- ☐ Create issue routes (issue.routes.ts):

```

GET    /api/issues

POST   /api/issues

GET    /api/issues/:id

PUT    /api/issues/:id

DELETE /api/issues/:id

PUT    /api/issues/:id/resolve

GET    /api/issues/export

```

- ☐ Create issue controller

- ☐ Test routes

**Day 2 (8 hours):**

- ☐ Create issue service (issue.service.ts):

- **Create issue:**

- Validate portfolio_id belongs to tenant

- Check for duplicate (same portfolio, same hour, same day)

- Create issue record with tenant_id

- Auto-add monitored_by to personnel list

- Release portfolio lock

- Log admin activity

- **Update issue:**

- Verify issue belongs to tenant

- Update fields

- Log changes

- **Delete issue:**

- Soft delete or hard delete

- Log deletion

- **List issues:**

- Filter by tenant_id

- Search functionality

- Pagination

- ☐ Test all issue operations

---

### Week 7, Day 3-5: Wednesday-Friday - Frontend Issue UI (24 hours)

**Day 3 (8 hours):**

- ☐ Create IssueForm.tsx (Log New Issue):

- Portfolio dropdown (searchable)

- Site input/dropdown

- Issue hour selector (0-23, auto-filled with current hour)

- Description textarea

- Issue type dropdown (optional)

- Severity dropdown (Low/Medium/High/Critical)

- Monitored by dropdown

- Missed by multi-select dropdown

- Attachments upload (optional)

- Notes textarea

- Submit button

- Cancel button

- ☐ Add form validation

- ☐ Test issue submission

**Day 4 (8 hours):**

- ☐ Create IssuesTable.tsx:

- Columns: Portfolio, Site, Hour, Description, Status, Monitored By, Missed By, Created At, Actions

- Sortable columns (click header to sort)

- Search bar (search across all fields)

- Filter dropdowns:

- Portfolio filter

- Status filter

- Date range filter

- Hour range filter

- Monitored by filter

- Pagination controls

- Export to Excel/CSV button

- Action buttons per row (View, Edit, Delete)

- ☐ Implement sorting, filtering, search

- ☐ Test table functionality

**Day 5 (8 hours):**

- ☐ Create IssueDetailsView.tsx (modal or page):

- Full issue information display

- Edit button

- Delete button

- Resolve/Close button

- Reopen button

- Add comment section

- Issue history/timeline

- Print button

- ☐ Create EditIssueModal.tsx:

- All fields editable

- Save changes button

- Cancel button

- Validation

- ☐ Test issue detail views

---

### Week 8, Day 1-2: Monday-Tuesday - Issue Advanced Features (16 hours)

**Day 1 (8 hours):**

- ☐ Implement issue search:

- Search by portfolio name

- Search by site name

- Search by description

- Search by monitored person

- Search by date

- Highlight search terms

- ☐ Implement filters:

- Date range picker

- Portfolio filter (multi-select)

- Status filter (multi-select)

- Hour range filter

- User filter

- ☐ Test search and filters

**Day 2 (8 hours):**

- ☐ Implement issue export:

- Export to Excel with formatting

- Export to CSV

- Export with current filters applied

- Include all columns

- Generate filename with date

- ☐ Create export service (exportUtils.ts)

- ☐ Test export functionality

---

### Week 8, Day 3-5: Wednesday-Friday - Issue Testing & Polish (24 hours)

**Day 3 (8 hours):**

- ☐ Test all issue features:

- Create issue

- Edit issue

- Delete issue

- Search issues

- Filter issues

- Sort issues

- Export issues

- Resolve issue

- View issue details

- ☐ Test tenant isolation (issues)

- ☐ Test duplicate prevention

**Day 4 (8 hours):**

- ☐ Add real-time features:

- Auto-refresh issue list (every 30 seconds)

- Live updates when new issue logged

- Notification when issue assigned to you

- ☐ Add validation:

- Prevent logging issue for same portfolio + same hour + same day

- Require description

- Validate hour (0-23)

- ☐ Fix bugs

**Day 5 (8 hours):**

- ☐ UI improvements:

- Loading states

- Error messages

- Success notifications

- Empty states

- Animations

- ☐ Write unit tests

- ☐ Write integration tests

- ☐ Code review

**Phase 6 Completion Checklist:**

- ✅ Issue CRUD working

- ✅ Issue search & filters functional

- ✅ Issue export working

- ✅ Real-time updates implemented

- ✅ Tenant isolation verified

- ✅ All tests passing

---

## **Phase 7: Analytics & Reporting (Week 9)**

**Duration:** 5 Business Days

**Team:** Full-stack Developer

**Deliverables:** Dashboard analytics, charts, heat maps

### Day 1: Monday - Backend Analytics API (8 hours)

**Morning (4 hours):**

- ☐ Create analytics routes (analytics.routes.ts):

```

GET /api/analytics/dashboard

GET /api/analytics/coverage

GET /api/analytics/performance

GET /api/analytics/users

GET /api/analytics/matrix

GET /api/analytics/trends

```

**Afternoon (4 hours):**

- ☐ Create analytics service (analytics.service.ts):

- Dashboard stats (total issues, portfolios with issues, avg hour)

- Hourly coverage (issues per hour 0-23)

- Performance metrics

- Issues by user

- Portfolio monitoring matrix

- Trend analysis

- ☐ Optimize queries for performance

- ☐ Test analytics endpoints

---

### Day 2: Tuesday - Dashboard Statistics (8 hours)

**Morning (4 hours):**

- ☐ Create Dashboard.tsx:

- Stats cards (7-column layout on desktop)

- Total Issues Count

- Portfolios with Issues

- Sites with Issues

- Average Issue Hour

- Real-time auto-refresh (30 seconds)

- Last updated timestamp

- ☐ Create StatsCard.tsx component

- ☐ Integrate with analytics API

**Afternoon (4 hours):**

- ☐ Create QuickActions.tsx:

- "Log New Issue" button

- "View All Issues" button

- "Hourly Coverage" button

- Hover effects

- ☐ Create RecentActivity.tsx:

- Recent issues (last 5)

- Recent admin actions (last 5)

- ☐ Test dashboard

---

### Day 3: Wednesday - Charts & Heat Maps (8 hours)

**Morning (4 hours):**

- ☐ Create HourlyCoverageChart.tsx:

- Bar chart showing issues per hour (0-23)

- Color-coded bars (green/yellow/red)

- Interactive tooltips

- Zoom/pan functionality

- ☐ Create IssuesChart.tsx:

- Line chart showing issues over time

- Filter by date range

- ☐ Install and configure Chart.js

**Afternoon (4 hours):**

- ☐ Create PortfolioStatusHeatMap.tsx:

- Grid showing all portfolios

- Color indicators (Green = checked, Red = issues, Gray = pending)

- Click to drill down

- Hover tooltips

- ☐ Create PortfolioHeatMap.tsx:

- Heat map showing coverage by hour

- Darker = more coverage

- Interactive

- ☐ Test all charts and heat maps

---

### Day 4: Thursday - Performance Analytics & Reports (8 hours)

**Morning (4 hours):**

- ☐ Create PerformanceAnalytics.tsx:

- Issues logged today/week/month

- Average response time

- Most problematic portfolios (top 10)

- Most active users

- Peak issue hours

- Resolution rate

- Custom date range selector

- ☐ Create charts for performance metrics

**Afternoon (4 hours):**

- ☐ Create IssuesByUser.tsx:

- Table: User | Issues Found | Issues Missed

- Performance leaderboard

- Filter by date range

- Export to Excel

- ☐ Create PortfolioMonitoringMatrix.tsx:

- Grid: Portfolios (rows) × Hours (columns 0-23)

- Cell colors: Green (checked), Red (issue), Gray (not checked)

- Click cell to view details

- Export to Excel

- ☐ Test all reports

---

### Day 5: Friday - Analytics Testing & Optimization (8 hours)

**Morning (4 hours):**

- ☐ Test all analytics features:

- Dashboard stats

- Hourly coverage chart

- Heat maps

- Performance analytics

- Issues by user

- Monitoring matrix

- ☐ Verify tenant isolation (analytics)

- ☐ Test with large datasets

**Afternoon (4 hours):**

- ☐ Optimize performance:

- Database query optimization

- Add caching where appropriate

- Lazy loading for charts

- Pagination for large reports

- ☐ UI polish:

- Loading states

- Empty states

- Error handling

- ☐ Write tests

- ☐ Code review

**Phase 7 Completion Checklist:**

- ✅ Dashboard with real-time stats

- ✅ All charts working

- ✅ Heat maps functional

- ✅ Performance analytics complete

- ✅ Reports with export capability

- ✅ Optimized for performance

---

## **Phase 8: Admin Panel & Super Admin (Week 10)**

**Duration:** 5 Business Days

**Team:** Full-stack Developer

**Deliverables:** Complete admin panel with all features

### Day 1: Monday - Admin Panel Structure (8 hours)

**Morning (4 hours):**

- ☐ Create AdminPanel.tsx (main component):

- Modal/page structure

- Tab navigation:

- Portfolios

- Login Users

- Monitored Personnel

- Active Locks

- Admin Logs

- Coverage Matrix

- Header with admin name

- Logout button

- Close button

**Afternoon (4 hours):**

- ☐ Create admin routes (admin.routes.ts):

```

GET    /api/admin/logs

POST   /api/admin/logs

GET    /api/admin/locks

DELETE /api/admin/locks/:id

GET    /api/admin/personnel

POST   /api/admin/personnel

DELETE /api/admin/personnel/:id

```

- ☐ Create admin controller & service

- ☐ Test admin endpoints

---

### Day 2: Tuesday - Admin Panel Tabs 1-3 (8 hours)

**Morning (4 hours):**

- ☐ **Portfolios Tab:**

- Add new portfolio form

- Existing portfolios list

- Edit portfolio (inline or modal)

- Delete portfolio (with confirmation)

- Duplicate name prevention

- ☐ **Login Users Tab:**

- Create new login user form (with email) ✅

- Existing users list

- Show credentials (copyable)

- Edit user

- Activate/Deactivate user

- Delete user

**Afternoon (4 hours):**

- ☐ **Monitored Personnel Tab:**

- Add new monitored person form

- Existing personnel list (grid view)

- Delete monitored person

- Sync with login users

- Auto-add from login users

- ☐ Test first 3 tabs

---

### Day 3: Wednesday - Admin Panel Tabs 4-6 (8 hours)

**Morning (4 hours):**

- ☐ **Active Locks Tab:**

- Table showing all active locks

- Columns: Portfolio, Locked By, Hour, Locked At, Expires At, Actions

- "Show expired locks" checkbox

- Admin unlock button (with confirmation)

- Real-time updates

- ☐ **Admin Logs Tab:**

- Add custom log note form

- Activity logs list (last 50)

- Color-coded by action type

- Filter by action type

- Auto-refresh

**Afternoon (4 hours):**

- ☐ **Coverage Matrix Tab:**

- Reuse PortfolioMonitoringMatrix component

- Filter by portfolio

- Filter by date

- Export to Excel

- ☐ Test last 3 tabs

---

### Day 4: Thursday - Super Admin Portal (8 hours)

**Morning (4 hours):**

- ☐ Create SuperAdminDashboard.tsx:

- Global statistics (all tenants)

- Total tenants, users, issues

- Most active tenants

- System health

- Revenue overview (if billing enabled)

- ☐ Create GlobalAnalytics.tsx:

- Charts showing system-wide metrics

- Tenant growth over time

- User growth over time

- Issues volume trends

**Afternoon (4 hours):**

- ☐ Create SystemMonitoring.tsx:

- API uptime

- Average response time

- Database performance

- Error rate

- Active sessions

- Real-time metrics

- ☐ Create BillingManagement.tsx (optional):

- Subscription plans

- Billing history

- Payment status

- ☐ Test super admin features

---

### Day 5: Friday - Admin Testing & Polish (8 hours)

**Morning (4 hours):**

- ☐ Test all admin features:

- All admin panel tabs

- Super admin dashboard

- Permissions (only admin can access)

- Tenant isolation (admin sees only their tenant)

- Super admin bypass (sees all tenants)

- ☐ Fix bugs

**Afternoon (4 hours):**

- ☐ UI polish:

- Loading states

- Error handling

- Success notifications

- Animations

- Responsive design (mobile-friendly)

- ☐ Write tests

- ☐ Code review

- ☐ Documentation

**Phase 8 Completion Checklist:**

- ✅ Admin panel fully functional

- ✅ All 6 tabs working

- ✅ Super admin portal complete

- ✅ Permissions enforced

- ✅ Tests passing

---

## **Phase 9: Testing & Quality Assurance (Week 11)**

**Duration:** 5 Business Days

**Team:** Full-stack Developer + QA (optional)

**Deliverables:** All tests passing, bug-free application

### Day 1: Monday - Unit Testing (8 hours)

**Morning (4 hours):**

- ☐ Write unit tests for backend:

- Auth service tests

- Tenant service tests

- Portfolio service tests

- Issue service tests

- Middleware tests

- Utility function tests

- ☐ Run tests: `npm test`

**Afternoon (4 hours):**

- ☐ Write unit tests for frontend:

- Component tests (React Testing Library)

- Hook tests

- Utility function tests

- API service tests (mock API)

- ☐ Run tests: `npm test`

- ☐ Aim for 80%+ code coverage

---

### Day 2: Tuesday - Integration Testing (8 hours)

**Morning (4 hours):**

- ☐ Write integration tests for API:

- Auth flow (register, login, logout)

- Portfolio CRUD operations

- Issue CRUD operations

- Tenant isolation verification

- Cross-tenant access prevention

- ☐ Use Supertest or similar

**Afternoon (4 hours):**

- ☐ Write integration tests for frontend:

- User flows (login → dashboard → log issue → logout)

- Form submissions

- Navigation

- State management

- ☐ Run all integration tests

---

### Day 3: Wednesday - End-to-End (E2E) Testing (8 hours)

**Morning (4 hours):**

- ☐ Setup E2E testing framework (Cypress or Playwright)

- ☐ Write E2E tests:

- **User Journey 1: User Login & Log Issue**

- User logs in with email ✅

- Navigates to dashboard

- Clicks "Log Issue"

- Fills form

- Submits

- Sees success message

- Issue appears in list

- **User Journey 2: Admin Adds Portfolio**

- Admin logs in

- Opens admin panel

- Adds new portfolio

- Portfolio appears in list

**Afternoon (4 hours):**

- ☐ Write more E2E tests:

- **User Journey 3: Tenant Isolation**

- User A (Tenant A) logs in

- Sees only Tenant A data

- Logs out

- User B (Tenant B) logs in

- Sees only Tenant B data

- **User Journey 4: Super Admin**

- Super admin logs in

- Creates new tenant

- Views all tenants

- Impersonates tenant admin

- Views tenant data

- ☐ Run all E2E tests

---

### Day 4: Thursday - Manual Testing & Bug Fixing (8 hours)

**Morning (4 hours):**

- ☐ Manual testing checklist:

- ☐ Test on Chrome

- ☐ Test on Firefox

- ☐ Test on Safari

- ☐ Test on Edge

- ☐ Test on mobile (responsive design)

- ☐ Test on tablet

- ☐ Test all user flows

- ☐ Test all admin features

- ☐ Document bugs found

**Afternoon (4 hours):**

- ☐ Fix critical bugs

- ☐ Fix high-priority bugs

- ☐ Fix medium-priority bugs

- ☐ Re-test after fixes

- ☐ Update test cases

---

### Day 5: Friday - Security Audit & Performance Testing (8 hours)

**Morning (4 hours):**

- ☐ Security testing:

- ☐ SQL injection attempts

- ☐ XSS (Cross-Site Scripting) attempts

- ☐ CSRF protection verification

- ☐ Authentication bypass attempts

- ☐ Cross-tenant access attempts

- ☐ Rate limiting verification

- ☐ Password security (hashing, strength)

- ☐ JWT token security

- ☐ HTTPS enforcement

- ☐ Use security scanning tools (OWASP ZAP, etc.)

- ☐ Fix security issues found

**Afternoon (4 hours):**

- ☐ Performance testing:

- ☐ Load testing (100+ concurrent users)

- ☐ API response time testing

- ☐ Database query performance

- ☐ Frontend bundle size check

- ☐ Image optimization

- ☐ Lighthouse score (aim for 90+)

- ☐ Optimize slow queries

- ☐ Optimize frontend performance

- ☐ Final code review

**Phase 9 Completion Checklist:**

- ✅ All unit tests passing

- ✅ All integration tests passing

- ✅ All E2E tests passing

- ✅ No critical bugs

- ✅ Security audit complete

- ✅ Performance optimized

- ✅ Ready for deployment

---

## **Phase 10: Deployment & Go-Live (Week 12)**

**Duration:** 5 Business Days

**Team:** Full-stack Developer + DevOps (optional)

**Deliverables:** Live production application

### Day 1: Monday - Production Environment Setup (8 hours)

**Morning (4 hours):**

- ☐ Create production Supabase project:

- Create new project (production)

- Run all migrations

- Setup Row Level Security

- Create indexes

- Configure backups (daily)

- Note production API keys

**Afternoon (4 hours):**

- ☐ Setup production environment variables:

- Frontend (.env.production):

- REACT_APP_API_URL

- REACT_APP_SUPABASE_URL

- REACT_APP_SUPABASE_ANON_KEY

- Backend (.env.production):

- SUPABASE_URL

- SUPABASE_SERVICE_KEY

- JWT_SECRET (strong random string)

- NODE_ENV=production

- ☐ Configure CORS for production

- ☐ Setup SSL/HTTPS certificates (automatic on Vercel/Railway)

---

### Day 2: Tuesday - Backend Deployment (8 hours)

**Morning (4 hours):**

- ☐ **Deploy to Railway:**

- Sign up for Railway (https://railway.app)

- Connect GitHub repository

- Create new project

- Deploy from GitHub (backend folder)

- Add environment variables

- Deploy

- Get production URL (e.g., https://your-app.railway.app)

- ☐ Test backend API (Postman)

**Afternoon (4 hours):**

- ☐ Configure production settings:

- Enable logging

- Setup error monitoring (Sentry, optional)

- Configure rate limiting

- Setup health check endpoint

- ☐ Test all API endpoints in production

- ☐ Verify database connection

- ☐ Test tenant isolation in production

---

### Day 3: Wednesday - Frontend Deployment (8 hours)

**Morning (4 hours):**

- ☐ **Deploy to Vercel:**

- Sign up for Vercel (https://vercel.com)

- Connect GitHub repository

- Import project (frontend folder)

- Configure build settings:

- Build Command: `npm run build`

- Output Directory: `build`

- Add environment variables

- Deploy

- Get production URL (e.g., https://your-app.vercel.app)

**Afternoon (4 hours):**

- ☐ Configure custom domain (optional):

- Purchase domain (e.g., yourapp.com)

- Configure DNS:

- A record: @ → Vercel IP

- CNAME record: www → cname.vercel-dns.com

- CNAME record: * → cname.vercel-dns.com (for subdomains)

- Add domain in Vercel

- Wait for SSL certificate (automatic)

- ☐ Test frontend in production

- ☐ Verify API integration

---

### Day 4: Thursday - Data Migration & Testing (8 hours)

**Morning (4 hours):**

- ☐ Migrate existing data (if any):

- Export data from current system

- Transform data (add tenant_id)

- Import into production database

- Verify data integrity

- Test queries with real data

- ☐ Create first production tenant:

- Use super admin to create tenant

- Create tenant admin user

- Test tenant login

**Afternoon (4 hours):**

- ☐ End-to-end testing in production:

- Test user registration/login (with email) ✅

- Test portfolio management

- Test issue tracking

- Test admin panel

- Test super admin features

- Test on multiple devices

- Test subdomain routing

- ☐ Fix any production issues

---

### Day 5: Friday - Go-Live Preparation & Launch (8 hours)

**Morning (4 hours):**

- ☐ Final checks:

- ☐ All features working

- ☐ No console errors

- ☐ No broken links

- ☐ All images loading

- ☐ SSL certificate valid

- ☐ Emails sending correctly

- ☐ Backups configured

- ☐ Monitoring enabled

- ☐ Create user documentation:

- User guide (how to use the app)

- Admin guide (how to manage tenants)

- FAQ

- ☐ Prepare launch announcement

**Afternoon (4 hours):**

- ☐ **GO LIVE! 🚀**

- ☐ Announce to stakeholders

- ☐ Onboard first clients:

- Create their tenants

- Send credentials

- Provide training (if needed)

- ☐ Monitor for issues:

- Check error logs

- Monitor API response times

- Watch for user feedback

- ☐ Celebrate! 🎉

**Phase 10 Completion Checklist:**

- ✅ Backend deployed to Railway

- ✅ Frontend deployed to Vercel

- ✅ Database migrated to production

- ✅ Custom domain configured (optional)

- ✅ All production tests passing

- ✅ Documentation complete

- ✅ Application LIVE!

---

## 📊 Resources & Team Allocation

### Recommended Team Structure

**Option 1: Lean Team (6-7 weeks)**

```

Team: 3 Developers

- 1 Senior Full-stack Developer (Lead)

- 1 Frontend Developer

- 1 Backend Developer

Timeline: 6-7 weeks

Cost: 3 × $5,000/month × 1.5 months = $22,500

```

**Option 2: Solo Developer (10 weeks)**

```

Team: 1 Full-stack Developer

Timeline: 10 weeks

Cost: 1 × $5,000/month × 2.5 months = $12,500

```

**Option 3: Accelerated (4-5 weeks)**

```

Team: 5 Developers

- 1 Tech Lead

- 2 Frontend Developers

- 2 Backend Developers

Timeline: 4-5 weeks

Cost: 5 × $5,000/month × 1.25 months = $31,250

```

---

## 💰 Cost Breakdown

### Infrastructure Costs (First Year)

| Item | Tier | Cost |

|------|------|------|

| **Vercel (Frontend)** | FREE | $0/month |

| **Railway (Backend)** | FREE | $0/month ($5 credit) |

| **Supabase (Database)** | FREE | $0/month (500MB) |

| **Domain** | Optional | $10-15/year |

| **SSL Certificate** | Included | $0/month |

| **Total Monthly** | | **$0/month** |

| **Total Year 1** | | **$0-15/year** |

**When to upgrade (20+ clients):**

- Supabase Pro: $25/month ($300/year)

- Railway Pro: $10/month ($120/year)

- **Total: $420/year**

### Development Costs

| Team Option | Duration | Cost Estimate |

|-------------|----------|---------------|

| Solo Developer | 10 weeks | $12,500 |

| Lean Team (3 devs) | 6-7 weeks | $22,500 |

| Accelerated (5 devs) | 4-5 weeks | $31,250 |

---

## 📈 Scaling Plan

### Phase 1: MVP (0-10 clients)

- FREE tier sufficient

- 1 developer for maintenance

- Monthly cost: $0

### Phase 2: Growth (10-50 clients)

- Upgrade to paid tiers

- 1-2 developers for support

- Monthly cost: $35 (infrastructure)

### Phase 3: Scale (50+ clients)

- Enterprise infrastructure

- Dedicated support team

- Monthly cost: $100-500 (depending on scale)

---

## ✅ Final Deliverables Checklist

### Application Features

- ✅ Email-based authentication (users & admins) ✅

- ✅ Multi-tenant with complete data isolation

- ✅ Portfolio management (with subtitle & site range)

- ✅ Issue tracking (full CRUD)

- ✅ Portfolio locking system

- ✅ "All Sites Checked" status tracking

- ✅ Admin panel (6 tabs)

- ✅ Super admin portal

- ✅ Dashboard with real-time stats

- ✅ Hourly coverage charts

- ✅ Performance analytics

- ✅ Heat maps (status & coverage)

- ✅ Portfolio monitoring matrix

- ✅ Issues by user report

- ✅ Export to Excel/CSV

- ✅ Search & filters

- ✅ Mobile responsive

- ✅ Real-time updates (auto-refresh)

### Documentation

- ✅ User guide

- ✅ Admin guide

- ✅ API documentation

- ✅ Database schema documentation

- ✅ Deployment guide

- ✅ Setup instructions

### Testing

- ✅ Unit tests (80%+ coverage)

- ✅ Integration tests

- ✅ E2E tests

- ✅ Security audit

- ✅ Performance testing

### Deployment

- ✅ Production environment (Vercel + Railway + Supabase)

- ✅ SSL/HTTPS enabled

- ✅ Custom domain configured (optional)

- ✅ Monitoring enabled

- ✅ Backups configured

---

## 🎯 Key Changes from Original Requirements

### ✅ Authentication Change Implemented:

**OLD:** Username-based login

**NEW:** ✅ Email-based login (as requested)

**Changes Made:**

1. Database: `users.email` column (instead of just username)

2. Frontend: Email input fields in login forms

3. Backend: Login validates by email

4. JWT token: Includes email

5. User registration: Requires email

6. Password reset: Uses email

---

## 📞 Communication Plan

### Weekly Status Updates

- **Monday:** Week planning & task assignment

- **Wednesday:** Mid-week progress review

- **Friday:** Week completion review & demo

### Deliverables to Manager

- Week 2: Database schema demo

- Week 4: Authentication system demo

- Week 6: Portfolio management demo

- Week 8: Issue tracking demo

- Week 10: Analytics demo

- Week 12: Go-live!

---

**Document Version:** 1.0

**Last Updated:** December 17, 2025

**Status:** Ready for Manager Review

---

**End of Document**